## Sheet1
BMC Library & Information Technology Services 5-Year Strategic Roadmap (FY20-FY24)
Strategic Area of Focus
| Project | Tactical Steps | Contact/PM | Start-Q | End-Q | Completed | Notes
I. Institutional/Organizational Priorities that Cross Strategic Areas of Focus
Diversity, Equity, and Inclusion
Our Work with Students (3.1)
|  | Review and improve Digital Scholarship Summer Fellows program to prioritize equity and inclusion (3.1.0.2) - now folded into 3.2 goals as ongoing practice | Alice McGrath | FY20 Q2 | FY24 Q4 | √
|  | Assess and Improve Equity in Hiring (3.1.1.1) - Participate in broader, longer-range institutional efforts to develop data gathering and analysis practices that would facilitate equity, inclusion, and anti-racism inquiries such as these (see goal 3.2 below) |  |  |  | √
|  | Assess and Improve Equity in Hiring (3.1.1.2) - Ensure all students have equitable access to LITS job opportunities by being more transparent about the student hiring process and available opportunities in LITS. We have created a centralized Student Employment in LITS web page (https://www.brynmawr.edu/lits/projects-and-partnerships/student-employment-lits) and adopted policies for keeping the page up-to-date, publicly posting opportunities in the Daily Digest and on social media, and standardizing hiring and advertising practices across LITS departments. | Camilla MacKay and LITS managers | FY20 Q3 | FY20 Q4 | √
|  | Actively Engage ALL Students (1.1.2.1) - Continue to develop and deliver programs that foster student engagement and learning about technology-, data-, and library-related topics and practices, in partnership with other BMC departments where appropriate (e.g., Digital Intensives, workshops, THRIVE curricular components, Wikipedia edit-a-thons, etc.). |  |  |  | √
|  | Actively Engage ALL Students (1.1.2.2) - Identify early interventions, including first-year experiences, that create bridges for incoming students, especially FGLI students and students who may not have experienced staffed libraries, so that everyone is aware of and can access the rich materials and support represented in the BMC Libraries as they embark on their scholarly careers and start to do college-level research. |  |  |  | √
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.1) - Continue to offer the cross-institutional Careers in Library and Information Science (CiLIS) bootcamp for students from underrepresented groups with interest in library and information science careers as part of developing a more diverse pipeline in these fields. |  | (Continuing) |  | √
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.2) - Continue our own equity, inclusion, and anti-racism professional development as staff so that we gain skill and proficiency as mentors for students of diverse backgrounds and identities. |  | (Continuing) |  | √
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.3) - Expand mentoring in deep technical skills to help empower students, especially BIPOC students and all women and gender non-conforming students. These groups are underrepresented in IT professions and these skills are important for potential future pathways. | Vince Patone/Enterprise Team | (Continuing)
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.4) - Educate ourselves about how to support LITS students in equitable and inclusive professional development models, including by learning from students and co-creating model work environments with them that they can take into their future endeavors. | Camilla MacKay/Kate Blinn/RIS | (Continuing) |  | √
Data and Assessment (3.2)
|  | Analyze MISO data disaggregated by race/ethnicity to assess whether we have disparities in levels of satisfaction or importance (positive outcome, further discussion and analysis will grow out of initial analysis) (3.2.1) - LITS already collects data from students and employees via the biannual MISO survey, regular service improvement feedback requests, and an annual faculty interview program. We’ll continue to gather, review, and act on this data. Our Director of Assessment and Assessment Working Group will guide our thinking about how to make meaningful use of these rich data sets and how to connect these data sources with disaggregated demographic data and more specific studies to inform our continuous movement toward equitable and inclusive programs, services, resources, and spaces. | Dave Consiglio and Assessment WG | FY21 Q4 | FY21 Q4 | √
Data and Assessment (3.2.2) - Examples of the kinds of questions we want to address include: Who is /is not participating in our Intensives, workshops, and other programs? Which students are / are not using the library? How do we gather data on those potential gaps and address any disparities that we find?
Data and Assessment (3.2.3) - We want to assess through a Racial Equity Impact Analysis our current practices for gathering feedback, asking such key questions as who are we talking to? how are we getting feedback? how do we portray our offerings for the community? Some of these are areas where representative focus groups may give us important perspective and insights.
Data and Assessment (3.2.4) - We’re interested in any insights we can gain from the College’s belongingness studies and campus climate studies, especially looking to the data for places where we can bridge gaps for Black, Indigenous, and other students of color.
Data and Assessment (3.2.5) - We believe in the power of stories in addition to the importance of aggregate data. We want to hear about impacts on students’ lives (positive and negative) of our offerings and their general experience of the College as they move through their educational journeys, and we hope those stories over time will show that the current high-priority College actions and local LITS actions land well and change students’ experiences for the better. We're interested in taking a pulse using appropriate psychology/affective measures to compare and contrast outcomes across groups and across time. How do we make sure our current and future efforts are landing with the concerns that community members are raising? What other data can we gather or draw upon to measure students’ sense of the impact of efforts underway at the institutional level and at the LITS level to see how the energy that’s invested is landing and to assess how we might need to shift course to meet our goals?
Data and Assessment (3.2.6) - We want to advocate for the College reviewing annually with the community how they are relating to our Equity, Inclusion, and Anti-Racism goals. Questions to ask might include: Did you engage with any of these initiatives? And did you find them valuable? Every year the College reports on initiatives in a more concerted way, and we're seeing a way we could take it to the next level with outreach and engagement to hear how initiatives are landing with those they’re designed to serve. Action Item: Gina will take these ideas to senior leadership.
|  | Data and Assessment (3.2.7) - Those who don't work actively with students in their regular work have a goal of volunteering to do senior exit interviews, recognizing that progress is seen in the eyes of the student and that listening to students in this annual process is a way to contribute to understanding from students’ perspectives how the College is doing. | Gina Siesing and all LITS staff | FY21 Q4 | FY21 Q4 (and subsequent years) | √
Description, Metadata and Cataloguing (3.3)
|  | Description, Metadata and Cataloguing (3.3.1) - We will continue to revise and augment the cataloguing and descriptive language that is used for our collections, working locally and in conjunction with consortial/regional and national efforts to update subject headings, as well as other classification terms and metadata, so that they are historically and culturally appropriate. This includes the removal of descriptors that are problematic and replacing them with updated and appropriate language; for example, TriCo librarians participated locally in making the change from “illegal aliens” to “undocumented immigrants” as part of a national movement to change this Library of Congress subject heading. |  |  |  | √
|  | Description, Metadata and Cataloguing (3.3.2) - We will support students’ development of ethical and technical facets of digital competencies as they work with us on projects to revise and augment metadata that enables discovery of our rich collections and further study of their complex contexts. An example in this context is the work of Special Collections cataloging the children’s book collection and engaging students in this project, using an anti-racist catalog as a guideline for the original descriptions in our metadata. |  |  |  | √
Description, Metadata and Cataloguing (3.3.3) - Tied to our next goal, we will review and enhance as needed the accessibility of our collection discovery platforms and finding aids, as well as the accessibility guidelines and implementation for the content stored within these platforms. We included robust accessibility review and enhancement into our recent implementation project for the TriCollege Libraries Digital Collections platform (https://digitalcollections.tricolib.brynmawr.edu/), and we will do the same for legacy and future platforms. An example of the way we would enhance accessibility of the collection objects within the platforms would be to ensure we have appropriate and descriptive metadata following WCAG guidelines, such as alt tags for images and other best practices.
Description, Metadata and Cataloguing (3.3.4) - We will articulate a series of defined projects to move this work forward and will partner with BMC grants officers to seek potential funding in support of this labor-intensive and important work.
Inclusive and Accessible Collections and Ongoing Research (3.4)
|  | Inclusive and Accessible Collections and Ongoing Research (3.4.1) - Special Collections is informing everything the department does with an equity, inclusion, and anti-racism lens. This year this includes ways of thinking about summer internships for students, framing of the fall exhibition, and how we build our collections. Special Collections will facilitate community engagement around our draft “Legacies of Colonialism and Racism in Special Collections” document in the upcoming year as a frame for demystifying the historical practices of special collections, making clear that special collections are open and welcoming and available for the full community to explore and study, and inviting in continuing research and learning projects around our phenomenal and complex collections and their contexts. |  |  |  | √
|  | Inclusive and Accessible Collections and Ongoing Research (3.4.2) - We’ll continue to acquire and highlight the work of diverse authors in our general library collections, as well as the work of BIPOC artists and makers and community members in our special collections. |  |  |  | √
|  | Inclusive and Accessible Collections and Ongoing Research (3.4.3) - We’ll continue to strengthen digital collections finding aids toward greater accessibility of collections. This work includes making more of the information we have public-facing and gathering more useful data surrounding the history of our collections and how they were acquired. This also includes creating new partnerships with communities represented in Bryn Mawr collections and collaborative continued research into the best practices for cultural representation, care, and preservation of collections from the perspective of their cultures of origin so we’re not just imposing ours. In each case, this will include determining if, and if so how, we care for a community’s materials in the Bryn Mawr collections. Alma/AchivesSpace integration complete FY23, enhancing access to finding aids and thereby collections. | FY21 Q1 | FY25 Q4
College Histories Projects (3.5)
|  | College Histories Projects (3.5.1) - Current projects include the Who Built Bryn Mawr? project, where LITS is a partner with the President’s Office; faculty in History and History of Art; Museum Studies; College Communications; and Alumnae/i Relations & Development; among others. The first phase of Who Built Bryn Mawr? was launched this year in Canaday Library and online, and next phases of which will continue this summer and beyond. This project ties to broader goals of surfacing, documenting, and publishing richer and more diverse stories of those who have been important to the formation of the College throughout its history and building our archives for future scholarship and discovery by way of documenting the collegiate experience from the student perspective. |  |  |  | √
|  | College Histories Projects (3.5.2) - Building digital collections is a priority for us, particularly archives that represent the collegiate experience from students’ perspectives. Recent projects include the Jewish Mawrters and Perry House oral histories projects and the Bryn Mawr Strike Collective digital collection. This includes proactively helping to archive the ephemeral, especially for the groups that weren’t part of dominant cultures at the time they participated as members of the Bryn Mawr College community. |  |  | (continuing) | √
|  | College Histories Projects (3.5.3) - We will continue to support innovative and sustainable forms of scholarly publishing and engaged conversation so that the research that is ongoing finds the broadest possible audience. One of the important benefits of the research into College histories is the chance for all of us – employees, students, alumnae/i, families, and friends of the College - is the chance to learn a lot of new and rich history that was not available prior to the research projects that students, faculty, and staff are conducting under the umbrella of College histories work. These are opportunities to expose parts of the unique collections of Bryn Mawr that have not been exposed, for those things that are exposed to be put into context, and also for us to expose gaps in the collections that also teach us and that in some cases we can remediate. |  |  | (continuing) | √
Accessibility (3.6)
|  | Accessibility (3.6.1) - We contributed in FY20 to articulation of the College’s new accessibility policy, and as next steps we’ll work to provide education around the policy and current accessibility standards to guide our implementation of tools, resources, and services in LITS. We’ll contribute as participants in the Accessibility Leadership Committee to articulating College standards for Universal Design for Learning (UDL) to guide the community in creating fully accessible and inclusive courses and learning experiences. Work on UDL policy was completed FY23, and the policy is posted on our website. Other facets of this work are ongoing. | Jenny Spohrer (EAST) | FY21 Q1 | FY23 Q2 | √
|  | Accessibility (3.6.2) - We will also share information about accessibility related to the tools we support for the community. Ongoing. | Grace Cipressi (EAST) | FY21 Q3 | FY23 Q4 | √
|  | Accessibility (3.6.3) - We will draw on accessibility expertise within LITS to review and update our published resources, such as the LITS web presence, LibGuides, our KnowledgeBase/Techdocs, Digital Collections, etc. As an example, for the Knowledge Base, AskAthena, we incorporated Accessibility best practices into the style guide as part of the Knowledge Owl/Ask Athena project ending FY23Q1-2. Ongoing we apply them as we create and maintain material. This is now a programmatic approach as new services are rolled out and as we review existing services. | Michael Harris (Web Services), et al. | FY21 Q1 | FY25 Q4
|  | Accessibility (3.6.4) - As a service enhancement in supporting students with disabilities, we plan to develop with the Dean’s Office proactive outreach to incoming students before they get to campus, including information about adaptive technologies they may need, resources available on campus, etc. | Grace Cipressi (EAST) | FY21 Q3 | FY24 Q2 | √
|  | Accessibility (3.6.5) - We will continue to play a leadership role in advocating for accessibility policies and practices for the College and expert staff will continue to provide accessibility consultation and support for colleagues across campus who are creating and adopting new tools or resources. Ongoing. | Grace Cipressi (EAST), Michael Harris (Web Services), et al. | FY21 Q1 | FY25 Q4 | √
|  | Accessibility (3.6.6) - We’ll continue to partner with College Communications to support accessibility of the College website. Ongoing. A related project was FY23 discovery to identify better tools for a) checking uploaded documents for accessibility and b) remediating inaccessible ones. These are being implemented in FY24. | Grace Cipressi, Michael Harris, Jenny Spohrer, Diggwynn Lobdell, et al. | FY21 Q1 | FY25 Q4 | √
|  | Accessibility (3.6.7) - We have audited the accessibility of many of our physical spaces, including the libraries, as part of an overall study conducted by the Accessibility Leadership Committee, and we will continue to work with Facilities Services and the Director of Access Services to enhance accessibility of physical spaces we manage. As we renovate spaces, we will pay particular attention to accessibility as a guiding principle. | Gina Siesing, Grace Cipressi, Jennifer Spohrer (LITS ALC members)
|  | Accessibility (3.6.8) -- Discover and implement better tool for checking and remediating accessibility of documents uploaded to Moodle. Primary goal was improving administrative interface and ability to collect and compile data about accessibility of documents at category level (e.g., SUBJ, term, etc.) to support new models for improving compliance. However, during discovery, we found that many tools could also replace the platform for converting documents from one format to another (e.g., from a PDF to a text-to-speech audio file) and greatly improve the visibility within Moodle and ease of use for students. This is what became the Yuja project. Discovery was AY23; currently in contract review; will start integration Fall 23, and hope to launch publicly in Jan 2024. | Grace Cipressi, EAST, Web | FY23Q1 | FY24Q4
|  | Accessibility (3.6.9) -- Analyze data on document accessibility collected through Yuja Panorama integration into Moodle and share with ALC to inform understanding of problem scope and development of institutional processes for improving compliance over time (e.g. getting department chairs involved, compiling and sharing data about changes from term-to-term, etc.) | Grace Cipressi, Jenny Spohrer | FY24Q3 | FY26Q4
Welcoming Spaces and Sense of Belonging (3.7)
|  | Welcoming Spaces and Sense of Belonging (3.7.1) - One of the ways we aim to ensure the libraries are welcoming spaces is by way of the displays of books in the libraries. These might include books by BIPOC authors, displays curated by students, and displays that recognize events like Banned Books Week, Black History Month, or Women's History Month. We are contributing to making other campus spaces more inclusive and welcoming, e.g., WBBM? in various campus buildings, Dalton archival image enhancements. Ongoing. | RIS, CEP, SpecColl | FY21 Q1 | FY25 Q4 | √
|  | Welcoming Spaces and Sense of Belonging (3.7.2) - Another way we aim to ensure our spaces are welcoming is by way of student-curated or co-curated exhibitions focusing on College histories. Key examples include the current Who Built Bryn Mawr? exhibition on the first floor of Canaday Library and Digital Color on Ancient Stone in the Carpenter Library Digital Media and Collaboration Lab, the installations associated with the renaming of Thomas Hall to Old Library, and the 2015 Backtalk: Exposures, Erasures, and Elisions of the Bryn Mawr College African Art Collections exhibition across the first-floor lobby, Class of 1912 Rare Book Room, and second-floor gallery of Canaday. These collections within our buildings and across campus will continue to be a major focus of our work helping to transform Bryn Mawr as a space. | SpecColl, RIS |  |  | √
|  | Welcoming Spaces and Sense of Belonging (3.7.3) - We aim to improve the public art displayed in the libraries and across campus, drawing on our Special Collections and the MakerSpace where community members are producing new work. Our Curator of Art and Artifacts will partner with colleagues across LITS and with community members to remove some of our collections from storage to meaningful display in our public spaces with a goal of giving Bryn Mawr public art increased attention and diversification. We’ll focus here on convening stakeholders to move such projects forward collaboratively, and we’ll also contribute to such projects convened by others such as the current Monument Lab partnership initiated by the President’s Office. | Carrie Robbins (SpecColl), et al. |  |  | √ | Updates to libraries, Dalton, etc.
|  | Welcoming Spaces and Sense of Belonging (3.7.4) - We will work actively to debunk the common perception that Special Collections are “special” in the sense of being secret, exclusionary, elitist, or otherwise inaccessible. The Bryn Mawr special collections are a teaching and learning collection that are treasures of the full community, stewarded by a multi-disciplinary team whose primary mission is to support meaningful community engagement with the collections, including through courses, research projects, guided tours, Friday Finds events where students and others share what they’ve discovered, etc. We are at the ready to provide orientation to special collections and the possibilities for working with these unique resources, and we will continue to engage the community proactively in thinking about the legacies, current state, and possible futures of the Bryn Mawr collections. |  |  |  | √
Welcoming Spaces and Sense of Belonging (3.7.5) - As information specialists, we are deeply aware of the ways words and semantic representation matter in creating inclusive or exclusive environments and resources, and we have a particular focus through the Information Literacy program led by Research and Instruction Libraries to support students in thinking about critical evaluation and constructive production of information sources. We will continue to expand our partnerships with academic programs to integrate information literacy into the curriculum in support of student research at all levels.
Accessible Resources (3.8)
|  | Accessible Resources (3.8.1) - We will continue to review community feedback and to make process improvements wherever we discover that there are barriers to accessing LITS resources or support. |  |  | (continuing) | √
Accessible Resources (3.8.2) - We will review our middleware platforms through which we create and distribute resources, including LibGuides, KnowledgeBase, and digital collections platforms – to ensure that these are accessible.
|  | Accessible Resources (3.8.3) - As we migrate to a new KnowledgeBase for how-to, support, and other help-oriented information, we will aim for the highest possible standard of accessibility and ease of discovery, following standards and enlisting the community in user experience testing with an eye to ensuring representation of underrepresented groups in our accessibility and usability reviews. |  |  |  | √
Accessible Resources (3.8.4) - Technology, software, and data are critical resources for the learning, teaching, research, and administrative work we do across the College. We will work to identify any places where community members have limited access to information technology resources and will do all we can to reach robust universal access. This includes accessibility and affordability of the resources, as well as the baseline of shared awareness of what is available and how to seek support in cases where resources are lacking or not obvious.
Inclusive and Accessible Programs (3.9)
|  | Inclusive and Accessible Programs (3.9.1) - We will regularly invite evaluation of programs we offer to seek suggestions of ways to improve program accessibility and inclusivity. |  |  |  | √
Inclusive and Accessible Programs (3.9.2) - We’ll review data about participation in programs such as Intensives in partnership with Career and Civic Engagement to determine whether there are any disparities in participation, whether based on race/ethnicity, socioeconomic status, or other factors. If we find disparities in participation or in outcomes related to our programming (digital competencies, information literacy, etc.), we will propose interventions to correct those disparities and will work with relevant stakeholders to ensure we’re closing the gap in ensuring more accessible, inclusive programs.
How We Invest our Budget Money (3.10)
|  | How We Invest our Budget Money (3.10.1) - We are currently integrating diversity, equity, and inclusion questions and review into our vendor evaluation and IT procurement processes. | Bill Kenny and LITS Managers | FY21Q1 | FY21Q4 | √
|  | How We Invest our Budget Money (3.10.2) - Within library acquisitions, we’ll integrate a new focus on purchasing books from Black-owned and other BIPOC-owned bookstores and will seek partnerships with local community bookstores. | Berry Chamness (CMD) |  |  | √
Digital Divide and Tech/Data/Information Justice (3.11)
|  | Digital Divide and Tech/Data/Information Justice (3.11.1) - We will integrate this digital/tech/data/information justice lens more specifically into the frameworks of our Digital Competencies and Information Literacy programs. In summer 2022, DSSF created a minimal computing/static website teaching toolkit which can introduce these ideas into digital assignments involving web design. Created new critical and inclusive design thinking workshop for DigiComp, added lens to web design and development workshops and intensives, etc. Have started incorporating into EAST consultations; broadened outreach over AY22-23; NOTE: as much an ecological issue as digital divide. For Information divide, continuing to focus on information literacy partnerships with Impact Center and scaffolding for all first-year students. We will bring this into the new FY24-25 project to refresh digital competencies as well, although it will go beyond that. | Jenny Spohrer (EAST) and Alex Pfundt (RIS) | FY23 Q1 | FY24 Q4 | √
|  | Digital Divide and Tech/Data/Information Justice (3.11.2) - We will educate students and community members about the non-neutrality of technology, data, and information and will integrate into our programs opportunities for engaging in anti-bias practices in the realms of technology, data, and information work. We will bring this into the new FY24-25 project to refresh digital competencies as well, although it will go beyond that. | Jenny Spohrer | FY23 Q1 | FY24 Q4
|  | Digital Divide and Tech/Data/Information Justice (3.11.3) - Across the disciplines of LITS, we are from professions where we think actively about these kinds of questions: what are the assumptions built into the resources we design, the tools we build? Where are the digital divide disparities within our own Bryn Mawr community, and how do we close those gaps? How can we influence broader technology, data, and information practices? Examples of topics might include data privacy issues, bias built into algorithms, and minimal computing possibilities (as one approach to address the digital divide and to model universal access to technology and data in an educational context). AI/Chat GPT may be a good nexus for some of this, and potential approaches include organizing a reading group/community of inquiry around this topic, mostly to meet internal needs/interests, potentially open to fac/staff, as well as students. | Jenny Spohrer, Camilla MacKay | FY24 Q2 | FY25 Q4
Digital Divide and Tech/Data/Information Justice (3.11.4) - We will hold LITS cross- discipline/cross-department think tanks around ethics and justice in tech/data/information and identify ways to educate about these issues and about justice-oriented practices. We would then want to design community intensives or teach-ins around these same issues and practices.
Transparency in our practices/communication (3.12)
|  | Transparency in our practices/communication (3.12.1) - Transparency in our practices and how we structure ourselves organizationally on the back-end to facilitate shared awareness and communication within LITS and for the broader community |  |  | (continuing) | √
|  | Transparency in our practices/communication (3.12.2) - Ways each team names intentions (communications and function) and plans -> accountability in the college -> sharing out our plans |  |  | (continuing) | √
|  | Transparency in our practices/communication (3.12.3) - Making sure we have a window into college administration |  |  | (continuing) | √
Transparency in our practices/communication (3.12.4) - Communicating in real time -> this can feel vulnerable vs. presenting polished final communications, but is a valuable long-term change
Transparency in our practices/communication (3.12.5) - Raise awareness for the EIAR efforts we’re making. Too often our efforts to advance anti-racism are not especially visible or transparent to the outside community. Gain advice from College Communications or the LITS CWG about how to de-clutter our websites and improve access to resources we already have but don’t necessarily make public (in Spec Coll, for example, resources for different types of research, materials handling, exhibition making, etc.)
Professional Development and Training (3.13)
|  | Professional Development and Training (3.13.0) - Develop curriculum of professional development for LITS staff - Initial DEIA/Anti-Racism Foundations sessions for departments (3.13.0) | DEI Team and CIO Direct Reports | FY20 Q4 | FY21 Q2 | √
|  | Professional Development and Training (3.13.1) - We have participated in past College professional development opportunities, such as the Race Matters Institute focus on staff recruitment, the Cornell Interactive Theatre Ensemble workshops on reducing implicit bias, and the Stir Fry seminar, and will continue to engage in these opportunities and to integrate what we learn into our local practices, as we have in updating our staff hiring practices and student employee hiring practices. Implicit Racial Bias and How You Can Stop It training with Racial Justice from the Heart + EQ for Inclusion and Equity with MCD. |  |  | (continuing) | √
Professional Development and Training (3.13.2) - Educating ourselves is key because of power we have in working relationships with students as employees, interns, and learners and because we serve a community of people who are different from ourselves and want to do that with awareness and skill. We also learn in deep ways from Bryn Mawr students and fellow employees, for example in the Trans 101, Religious Literacy, and Dialogues on Race learning opportunities offered by students and in Teach-ins and Community Days of Learning in student-led and staff-led sessions.
|  | Professional Development and Training (3.13.3) - We are committed to sharing our understanding of best practices in equity, inclusion, and anti-racism with student employees through our training for them as part of their jobs and committed to partnering with student employees to create robust and trustworthy channels for them to provide feedback to their supervisors toward enhancing the equity, inclusiveness, and intersectional anti-racism of their work environments. We aspire to co-create model work environments that students will want to replicate as they move out into their future careers. |  |  | (continuing) | √
|  | Professional Development and Training (3.13.4) - As we engage in shared professional development in facets of equity, inclusion, and intersectional anti-racism, we will continue to identify how equity, inclusion, and anti-racism goals of the College connect directly or indirectly with each of our jobs and service areas. |  |  | (continuing) | √
|  | Professional Development and Training (3.13.5) - One facet of our professional development will be learning about College histories through the projects LITS supports as a way to serve as resources who can help disseminate this new information with those we work with across campus and beyond. |  |  | (continuing) | √
Reducing our own marginalization as staff within the caste system of the College (3.14)
Reducing our own marginalization as staff (3.14.1) - Even as we at LITS invest our efforts in helping to make the College a more inclusive, equitable, and anti-racist institution for its students and faculty and full community, we will be mindful of the position of staff within the traditional caste hierarchies of Bryn Mawr and higher education more generally and will advocate for the recognition of our worth within the College, for respectful interactions across roles, and for equitable pay and benefits and inclusion for staff in College policies, practices, and culture.
|  | Review and improve LITS staff recruiting and hiring practices (work with Race Matters Institute (RMI) and HR and contributions to new Staff Recruitment Guidebook with diversity, equity, and inclusion lens; preparation for hiring managers and search committees with new College guidance | DEI Team and LITS managers | FY20 Q1 | FY20 Q4 | √
Information Security and Stewardship
|  | Update Incident Response Protocol | Gina Siesing | FY20 Q1 | FY20 Q2 | √
|  | Enhance/redesign Information Security Education Program | Melissa Cresswell | FY20 Q4 | FY21Q4 | √
|  | Conduct GLBA assessment in partnership with Controller's Office and Enrollment | Vince Patone | FY23 Q3 | FY24 Q1 | √
|  | Conduct internal and external penetration testing by way of external partner - both in service of GLBA assessment and as part of annual cycle | Vince Patone | FY23 Q4 | FY24 Q1 | √
|  | Implement vulnerability testing for infrastructure and systems | Vince Patone | FY20 Q3 | FY21 Q2 | √
|  | Complete whole disk encryption rollout | Katie Surkin | FY20 Q1 | FY23 Q4 | √
|  | Conduct discovery for network segmentation to address vulnerabilities posed by Internet of Things (IoT) devices and other desired uses of the network and provide data about models and costs - in partnership with Facilities, Campus Safety, research faculty/CLIC, and F&A | Vince Patone | FY24 Q1 | FY25 Q2
|  | Facilitate Ransomware Exercise for BMC | Melissa Cresswell | FY22 Q2 | FY22 Q4 | √
Holistic Mentorship and Professional Development of Students
|  | Continue to articulate student employment as professional development (including Digital Competencies and Information Literacy development). Annual professional development event for all LITS students. | Katie Surkin, Laura Surtees, Jenny Spohrer, and student employee supervisors across LITS | FY20 Q2 | FY22 Q4 | √
|  | Mentor students in internships and research projects (Educational Technology Interns, Digital Scholarship Fellows and Graduate Assistants, Histories of the College projects, etc.) | LITS managers with mentors across LITS | FY20 Q1 | FY24 Q4 | √
|  | Implement and assess split fellowship/service model for Digital Scholarship Graduate Assistants program | Alice McGrath | FY20 Q1 | FY20 Q4 | √
|  | Partner with Career & Civic Engagement Center to scaffold student reflection and articulation practices; using Domain of One's Own host eportfolios | Jenny Spohrer | FY20 Q1 | FY24 Q4
|  | Contribute to Customs, ESem, THRIVE, 360°, POSSE, and Advising programs | LITS managers and staff across teams | FY20 Q1 | FY24 Q4 | √
Planning and Organizational Development
|  | Develop 5-year Strategic Roadmap for LITS | Gina Siesing | FY19 Q3 | FY20 Q2 | √
|  | Develop local strategic plans within Enterprise, CEP, and TLR | Vince Patone, Melissa Cresswell, TLR Leadership Team | FY20 Q3 | FY21 Q1 | √
|  | Re-activate quarterly BMC senior staff prioritizing meetings as part of maintaining up-to-date strategic plan (delayed to FY22 following pandemic disruptions) | Gina Siesing | FY20 Q3 | FY21 Q1 | √
|  | Focus on service portfolio management practices (service design and enhancement, service assessment, service sunsetting) | Melissa Cresswell | FY20 Q2 | FY21 Q4 | √
|  | Leadership and professional development targeted to goals for the organization and staff | Gina Siesing | FY20 Q1 | FY24 Q4 | √
|  | Succession planning for LITS | Gina Siesing | FY20 Q2 | (ongoing) | √
II. Teaching, Learning, and Research
Canaday Library Renovation
|  | Pre-planning with LITS -> Deliver Vision Statement and Business Case to President Cassidy | Gina Siesing/Eric Pumroy | FY18 Q2 | FY20 Q1 | √
|  | Case study within broader campus space planning study led by Nina Bisbee/Facilities with external consultants | Gina Siesing with Berry Chamness, Eric Pumroy, and Katie Surkin | FY20 Q1 | FY20 Q4 | √
|  | Evaluating, cataloging, and re-housing of art works, artifacts, rare books, manuscripts & archives in anticipation of move, and seeking funding for this work | Eric Pumroy | FY20 Q1 | FY24 Q4 | On hold during pandemic and while we assess how presidential transition will affect likely timeline.
|  | Planning for special collections storage and exhibition spaces in new building | Eric Pumroy | FY20 Q1 | FY24 Q4 | On hold during pandemic and while we assess how presidential transition will affect likely timeline.
|  | Program design and concept design for Canaday | Gina Siesing | FY21 Q3 | FY22 Q2 | On hold during pandemic and while we assess how presidential transition will affect likely timeline.
|  | Fundraising for Canaday renovation as part of College campaign | Gina Siesing | FY22 Q2 | FY24 Q4 | On hold during pandemic and while we assess how presidential transition will affect likely timeline.
|  | Renovation of the library | Gina Siesing | FY24 Q1 | FY25 Q1 | On hold during pandemic and while we assess how presidential transition will affect likely timeline.
Data Science Program Support
|  | Discovery for Data Science Program Support (classroom/lab needs assessment; RStudio pilots; LITS role in lab support) | Jenny Spohrer | FY20 Q1 | FY20 Q4 | √
|  | Join GitHub Campus Program (including outreach/training benefits) - Joining is complete; outreach development has started, but will be slow and have a long tail. New DS position will help significantly. | Jenny Spohrer | FY20 | FY24 Q1 | √
|  | Service Modeling/Planning for Data Science Program Support (Jupyter/RStudio Service Modeling, planning classroom/lab renovation) - Once we have Rstudio Cloud and GitHub Campus in place, can start exploring whether these can be replacement for JupyterHub for Python-based TL | Jenny Spohrer | FY24 Q1 | FY25 Q4 | √
|  | RStudio Cloud license pilot (replacing RStudio Server pilot with more sustainable and more teaching-aligned cloud-based service) | Jenny Spohrer | FY22 Q4 | FY23 Q4 | √
|  | Classroom/lab space renovation as needed | Dave Consiglio | FY21 Q2 | FY22 Q2 | √
|  | Partner with Data Science Program Director on Needs Assessment, Articulating Data Science Program Resource Needs (Software, Equipment, Datasets, Infrastructure Services, and Staff Expertise), and Participate in Advocating for Necessary Resources to Create Robust Cross-disciplinary Infrastructure Support for the Program - Phase 1 complete resulting in new Data Science Coordinator position, a known service gap around STEM research technology services, and some initial broadly adaptable services - RStudio Cloud, Jupyter Hub. Phase 2 will be guided by Data Science Steering Committee with LITS support | Jenny Spohrer with LITS colleagues in data-related roles | FY22 Q3 | FY23 Q4 | √
|  | Service planning for LITS role in Lab/Center Support (if needed) | Jenny Spohrer/Dave Consiglio/Kate Blinn | FY21 Q2 | FY23 Q2 | √
|  | Recruit, onboard, and build service portfolio for a Data Science Education Support team member in EAST. | Jenny Spohrer | FY24Q2 | FY25Q4
|  | Integrating data science education in Digital Scholarship Program (data ethics, collections as data projects, programming support) | Alice McGrath | FY21 Q2 | FY25 Q1
Digital Asset Management and Preservation
|  | Implement Islandora as primary TriCo digital asset management and preservation platform (migrate from ContentDM and DSpace legacy systems) | Natalie Shilstut | FY20 Q2 | FY21 Q3 | √
|  | Electronic records management policy drafted and implemented | Allison Mills | FY20 Q1 | FY22 Q4 | √
|  | Implementing the Digital Preservation Policy | Natalie Shilstut | FY20 Q4 | FY22 Q4 | √
|  | EmbARK software update and migration to new servers | Howard Ding/Joanna Davidson | FY20 Q3 | FY20 Q4 | √
|  | Create infrastructure to support short and medium-term digital projects related to the History of the College | Alicia Peaker | FY20 Q3 | FY20 Q4 | √
|  | Drafting and implementing the digital projects sunsetting policy | Alice McGrath | FY20 Q3 | FY21 Q2 | √
|  | Migration from Islandora 7 to Islandora 9 (now called "Islandora 2," built on Drupal 9) and sunsetting of ContentDM | Jessica Bright, Howard Ding, Laurin Penland with TriCo colleagues | FY22 Q4 | FY24 Q2 | √
|  | Migration from DSpace to Islandora and sunsetting of DSpace | Jessica Bright, Howard Ding, Laurin Penland with TriCo colleagues | FY24 Q3 | FY25 Q3
|  | Additional migrations from various platforms (e.g., bepress) to consolidate our digital assets | Gina Siesing with TriCo Library Director Counterparts | FY25 Q1 | FY25 Q4
Digital Competencies for BMC Students
|  | Iteratively refine Digital Intensives offerings, adding one on Web Design and Development, aligning with Center for CCE Career Exploration focus | Jenny Spohrer | FY20 Q1 | FY20 Q4 | √
|  | Collaborate with departments and programs to integrate digital scholarship into curricula. Ongoing. Alice and team will continue to carve out time for this outreach. History has been our biggest success. We're still prioritizing it, although it is business as usual at this point. | Alice McGrath | FY20 Q2 | FY24 Q4 | √
|  | Provide opportunities for students to showcase their digital scholarship research at the Digital Scholarship Summer Symposium and other venues (these opportunities have become a routine part of the DS program) | Alice McGrath | FY20 Q1 | FY24 Q4 | √
|  | Expand programming integration with Civic Engagement/Praxis/Summer of Service | Jenny Spohrer | FY20 Q1 | FY21 Q2 | √
|  | Iteratively test, refine and get stakeholder feedback on Digital Competencies articulation rubric | Jenny Spohrer | FY21 Q1 | FY21 Q4 | √
|  | Expand training and outreach for Domain of One's Own | Alice McGrath | FY20 Q1 | FY24 Q4
|  | Integrate opportunities into Digital Competencies website via navigation to examples of different genres of opportunity with associated news stories | Jenny Spohrer | FY21 Q2 | FY23 Q2 | √
|  | Develop and pilot menu of digital competency-related workshops that can be offered in classes and outreach for LITS workshop services | Jenny Spohrer | FY21 Q1 | FY21 Q4 | √
|  | Scale/implement Digital Competencies articulation rubric | Jenny Spohrer | FY22 Q1 | FY22 Q4 | on hold in favor of larger related priorities
|  | Develop/plan half-semester and Praxis opportunities that involve Digital Competencies (e.g., graphic design, working with data, serious games) | Jenny Spohrer | FY20 Q3 | FY23 Q4 | √
|  | In partnership with Career and Civic Engagement, experiment with new models for offering and engaging students in digital intensive programming, including offering digital storytelling intensive for PE/wellness credit (winter 23-24) and a Praxis seminar on Data Analysis with Excel (AY24-25) in which students build and share data skills through internship with non-profits. | Chris Boyland, Jenny Spohrer | FY23 Q2 | FY25Q4
|  | Develop and host personal digital archiving workshops for students and student groups | Allison Mills, Jessica Bright | FY22 Q3 | FY24 Q4
Enable Contemporary Forms of Scholarship
|  | Facilitate interdisciplinary communities of learning and practice for digital scholarship | Alice McGrath | FY20 Q1 | FY24 Q4
|  | Build capacity for supporting emerging research technologies and methods through staff training | Vince Patone/Jenny Spohrer | FY20 Q2 | FY24 Q4
|  | Partner with campus groups to support public-facing and social-justice-oriented research projects | Eric Pumroy | FY20 Q2 | FY22 Q4
|  | Grow Digital Scholarship Research Institute for Tri-Co faculty to build skills and community (originated by Alicia Peaker; upcoming phase led by Mike Zarafonetis at HC; now led by Alice McGrath) | Alice McGrath | FY20 Q1 | FY24 Q4 | √
|  | Support faculty, staff, and graduate students in improving digital teaching, learning, and research activities through the Digital Bryn Mawr seed grant program. Ongoing program. | Jenny Spohrer | FY20 Q1 | FY24 Q4 | √
Information Literacy at Scale for BMC Students
|  | Expand structured opportunities for students (from introductions to library work for first-year students to IL learning for students within their majors) - Jennifer partners with Dean's Office and coordinates RIS librarians in introducing students to the library through videos, tutorials, customs week events. Ongoing student-led tours of the library; Zotero workshops taught by grad students | Jennifer Coval, RIS | FY20 Q1 | FY24 Q4 | √
|  | Advocate for pre-major focus via transformation of Esem or similar curricular intervention building on support of Curriculum Committee and Department Chairs | Camilla MacKay, Kate Blinn, RIS | FY20 Q3 | FY24 Q4
Lecture Capture
|  | Replace Tegrity (end of life) | Jenny Spohrer | FY19 Q3 | FY20 Q2 | √
|  | Panopto lecture capture system implementation | Vickie Karasic | FY20 Q2 | FY21 Q1 | √
Collier Phase Two Renovation
|  | LITS planning with Facilities department and architects | Gina Siesing/Camilla MacKay | FY20 Q1 | FY20 Q2 | √
|  | Preparation for construction: withdrawal/moving of library collections | Berry Chamness | FY21 Q3 | FY21 Q4 | √
|  | Collier construction | Gina Siesing/Camilla MacKay | FY22 Q1 | FY26 Q1 | Schedule delayed again due to supply chain issues
Moodle Future-Proofing and Planning
|  | Moodle MFA | Jenny Spohrer | FY19 Q1 | FY21 Q1 | √
|  | Internal service modeling to develop more sustainable support services and management plan | Jenny Spohrer | FY20 Q3 | FY21 Q2 | √
|  | Exploration of data analysis tools and integrations | Jenny Spohrer | FY21 Q2 | FY25 Q1
|  | Moodle Service Redesign Part 2 (final steps needed to move to persistant application service model and sustainable data/content management) | Jenny Spohrer | FY23 Q1 | FY24 Q2
Material Culture
|  | Develop guide to teaching primary source literacy | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Articulate options for teaching with collections | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Develop model for advising on exhibitions across campus | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Develop opportunities for students to have longer-term engagement with collections through post-bac program | Eric Pumroy | FY21 Q1 | FY22 Q4
|  | Design and Implement Critical Making initiative | Jenny Spohrer, Bronwen Densmore, EAST | FY24 Q2 | FY25 Q1
College History
|  | Oral History Guideines | Eric Pumroy | FY20 Q2 | FY20 Q4 | √
|  | Praxis or 360 Project - Develop guidelines for course-connected projects in the College Archives & identify potential projects - transformed to WBBM? Etc. | Eric Pumroy/Allison Mills | FY20 Q2 | FY21 Q4 | √
|  | Revise records management policy | Allison Mills | FY20 Q1 | FY20 Q4 | √
Continue to ensure stability and discoverability of collections
|  | Integrate Islandora with Primo/Alma | Howard Ding/Joanna Davidson | FY22 Q3 | FY23 Q1 | √
|  | ArchivesSpace upgrade | Howard Ding | FY20 Q1 | FY20 Q3 | √
|  | Integrate Islandora with ArchivesSpace | Howard Ding/Joanna Davidson | FY22 Q3 | FY23 Q1 | √
III. Enterprise Data, Systems, and Interfaces
Next-Generation Enterprise Ecosystem for Bryn Mawr
|  | Continued review of Core ERP terrain (particular focus on SIS developments) | Vince Patone | FY19 Q1 | FY22 Q4 | √
|  | Enrollment Discovery and Planning | Gina Siesing | FY19 Q3 | FY19 Q4 | √
|  | PowerFAIDS implementation for Financial Aid with associated data integrations and business process enhancements | David Sturgis | FY20 Q1 | FY20 Q2 | √
|  | ARD Discovery and Planning | Gina Siesing | FY19 Q4 | FY20 Q4 | √
|  | PeopleSoft Logging - Data about What's Currently Happening | Vince Patone | FY19 Q3 | FY20 Q4 | √
|  | PeopleTools 8.5.7 Upgrade | David Sturgis | FY21 Q1 | FY21 Q3 | √
|  | Evaluation and Selection of Alumnae/i Relations and Fund-raising platform(s) | Vince Patone | FY21 Q1 | FY21 Q1 | √
|  | Implementation planning for ARD with selected vendor | Vince Patone | FY21 Q2 | FY21 Q3 | √
|  | Implementation and Migration for ARD with associated data integrations and business process enhancements | Vince Patone | FY21 Q3 | FY22 Q2 | √
|  | Implement Identity Automation for provisioning and authorization | David Sturgis/Aaron Tsay | FY22 Q2 | FY24 Q2
|  | Evaluation and Selection of Core ERP (HR/Payroll/Finance/SIS+) and BiCo Strategic Planning for SIS | Vince Patone/Gina Siesing | FY22 Q1 | FY24 Q4
|  | PeopleSoft HCM Fluid Interface Discovery | David Sturgis | FY21 Q3 | FY22 Q1 | √
|  | PeopleTools 8.6.0 Upgrade and Fluid Interface Implementation | David Sturgis | FY23 Q4 | FY25 Q1
|  | PowerFAIDS Upgrade - early adoption underway and movement to cloud will be guided by new Director of Financial Aid | David Sturgis | FY23 Q1 | FY24 Q4
|  | Implementation of HR/Payroll/Finance modules of ERP | David Sturgis | FY25 Q1 | FY26 Q3
|  | Develop strategy for SIS with Haverford | Gina Siesing | FY23 Q3 | FY26 Q3
|  | Implement shared next-gen BiCo SIS model | Gina Siesing | FY26 Q4 | FY27 Q4
Data Governance and Business Intelligence
|  | Data/system Inventory update with ISC | Gina Siesing | FY19 Q3 | FY20 Q1 | √
|  | Data analytics introduction with Senior Staff | Gina Siesing | FY19 Q4 | FY19 Q4 | √
|  | Support ED for Institutional Effectiveness, Planning, and Research as she leads articulation of Institutional Data Governance Model | Gina Siesing, David Sturgis, Vince Patone, Dave Consiglio | TBD | TBD | Now responsibility of ED for IR
|  | Support ED for Institutional Effectiveness, Planning, and Research in evaluating data analytics and business intelligence solutions to match institutional and operational goals and developing and piloting dashboards for data reporting/analytics as part of next-gen enterprise implementation | Gina Siesing, David Sturgis, Vince Patone, Dave Consiglio | TBD | TBD | Now responsibility of ED for IR
|  | Support ED for Instituational Assessment, Planning, and Research in implementing data analytics and BI service including campus education model (LITS will partner to support data strategy articulated by ED for IR) | Gina Siesing, David Sturgis, Vince Patone, Dave Consiglio | TBD | TBD | Now responsibility of ED for IR
Web and Mobile Interfaces
|  | Support College website redesign project via ESC and core project team participation | Diggwynn Lobdell | FY20 Q1 | FY22 Q3 | √
|  | Website infrastructure upgrade - migrate our current Drupal installation to the BMC VMWare environment [We migrated instead to cloud hosting via Acquia to support business continuity.] | Diggwynn Lobdell | FY20 Q2 | FY20 Q4 | √
|  | Migration from Drupal 7 to Drupal 9 during or subsequent to College website redesign project | Diggwynn Lobdell | FY20 Q4 | FY22 Q4 | √
|  | TriCo Course Data - Store data in BMC Drupal instance and create BMC URL for students (Registrar's Office) | Vince Patone | FY20 Q3 | FY21 Q1 | √
|  | Migrate Find directory to Drupal - includes faculty CVs (Provost's Office) | Diggwynn Lobdell | FY20 Q3 | FY21 Q1 | √
|  | Retire bascom legacy web server with appropriate community engagement | Diggwynn Lobdell | FY21 Q2 | FY23 Q1 | √
|  | Review business case for implementing PeopleSoft Fluid | David Sturgis | FY20 Q2 | FY20 Q3 | √
|  | Implement PeopleSoft Fluid for SIS if business case compelling [Fluid will be required with next upgrade cycle.] | David Sturgis | FY21 Q1 | FY21 Q3 | √
|  | Assess other strategic mobile interface enhancement needs for BMC | Diggwynn Lobdell | FY21 Q4 | FY22 Q2
|  | Develop roadmap for any BMC mobile projects identified through assessment | Diggwynn Lobdell | FY22 Q3 | FY22 Q4
|  | Continue to assess and improve accessibility throughout all campus computing systems | Diggwynn Lobdell and Michael Harris | FY20 Q1 | FY24 Q4
Storage
|  | Implement TriCo Storage (digital asset preservation storage, access storage, and temporary workflow storage) | David Bertagni | FY20 Q2 | FY20 Q3 | √
Overall Infrastructure
|  | Review Infrastructure and Systems current state and develop strategic roadmap for future updates and investments (BMC), Phase I - complete refresh of SAN, VMWare, and Backup systems | Vince Patone | FY21 Q1 | FY24 Q2
|  | Review Infrastructure and Systems current state and develop strategic roadmap for future updates and investments (BMC), Phase II - Strategic review with focus on cloud strategy, network architecture, and meeting future BMC needs | Vince Patone and new Senior Manager for Infrastructure & Systems | FY24 Q3 | FY25 Q2
|  | Review Infrastructure and Systems current state and develop strategic roadmap for future I&S services model for TriCo Libraries | Gina Siesing in partnership with TriCo directors and CIOs | FY25 Q1 | FY25 Q4
IV. Client Experience and Support
Create seamless support for clients
|  | Service Experience and Delivery Team identifies a simple set of expectations and practices around which we can orient our approach to service | Katie Surkin | FY19 Q4 | FY21 Q4 | √
|  | Based on regular analysis of client feedback identify service experience enhancement projects | Katie Surkin | FY21 Q1 | FY24 Q4 | √
Develop robust consultation services for academic and administrative colleagues across campus
|  | Business Analysis and Solutions Team builds existing and potential consultative practices to maturity and defines service model across various LITS contexts | Melissa Cresswell | FY19 Q4 | FY20 Q4 | √
|  | Introduce LITS Academic Department/Program Visits model (building on suggestion from CLIC) | Gina Siesing/Jennifer Spohrer | FY22 Q3 | FY 23 Q4 | √
Help the community to navigate a fast-evolving technology terrain
|  | Help the community become increasingly comfortable and empowered using technology (outreach, peer-to-peer learning opportunities) | Melissa Cresswell | FY22 Q3 | FY24 Q4
|  | Streamline and humanize the client support experience and increase engagement with next generation models and tools (knowledge base, ticketing, ITSM/PPM, service catalog, in-time support innovations) | Melissa Cresswell | FY20 Q3 | FY25 Q4
|  | Build and enact models for systematically gathering feedback from the community (i.e. listening tour, ticket surveys) | Melissa Cresswell/Katie Surkin | FY20Q1 | FY21 Q2 | √
|  | Update endpoint security approach to include NextGen antivirus and enhanced threat detection and response | Melissa Cresswell/Katie Surkin | FY23 Q1 | FY24 Q4
Identify opportunities for innovative, efficient, and sustainable service delivery
|  | Analyze and enhance flexibilty and affordability in desktop hardware (procurement models and computer replacement program) | Bill Kenny | FY20 Q2 | FY24 Q2
|  | Move to next generation software delivery (virtualization, Windows management, Microsoft 365 deployment, lab environments) | Kordell Alexander | FY20 Q4 | FY25 Q4
|  | Stabilize and right-size software portfolio with updated budget model and sustainable approach to pilots and sunsets | Melissa Cresswell | FY24 Q3 | FY25 Q4
|  | Expand A/V funding model to include all teaching spaces; increase transparency, awareness, and sustainability of program and associated policies | Dave Consiglio | FY24 Q1 | FY24 Q4