## Sheet1
BMC Library & Information Technology Services 5-Year Strategic Roadmap (FY20-FY24)
Strategic Area of Focus
| Project | Tactical Steps | Contact/PM | Start-Q | End-Q | Completed | Estimated One-Time Costs | Estimated Ongoing Costs
I. Institutional/Organizational Priorities that Cross Strategic Areas of Focus
Diversity, Equity, and Inclusion
Our Work with Students (3.1)
|  | Review and improve Digital Scholarship Summer Fellows program to prioritize equity and inclusion (3.1.0.2) | Alice McGrath | FY20 Q2 | FY24 Q4
Assess and Improve Equity in Hiring (3.1.1.1) - Participate in broader, longer-range institutional efforts to develop data gathering and analysis practices that would facilitate equity, inclusion, and anti-racism inquiries such as these (see goal 3.2 below)
|  | Assess and Improve Equity in Hiring (3.1.1.2) - Ensure all students have equitable access to LITS job opportunities by being more transparent about the student hiring process and available opportunities in LITS. We have created a centralized Student Employment in LITS web page (https://www.brynmawr.edu/lits/projects-and-partnerships/student-employment-lits) and adopted policies for keeping the page up-to-date, publicly posting opportunities in the Daily Digest and on social media, and standardizing hiring and advertising practices across LITS departments. | Camilla MacKay and LITS managers | FY20 Q3 | FY20 Q4 | √
Actively Engage ALL Students (1.1.2.1) - Continue to develop and deliver programs that foster student engagement and learning about technology-, data-, and library-related topics and practices, in partnership with other BMC departments where appropriate (e.g., Digital Intensives, workshops, THRIVE curricular components, Wikipedia edit-a-thons, etc.).
Actively Engage ALL Students (1.1.2.2) - Identify early interventions, including first-year experiences, that create bridges for incoming students, especially FGLI students and students who may not have experienced staffed libraries, so that everyone is aware of and can access the rich materials and support represented in the BMC Libraries as they embark on their scholarly careers and start to do college-level research.
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.1) - Continue to offer the cross-institutional Careers in Library and Information Science (CiLIS) bootcamp for students from underrepresented groups with interest in library and information science careers as part of developing a more diverse pipeline in these fields. |  | (Continuing)
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.2) - Continue our own equity, inclusion, and anti-racism professional development as staff so that we gain skill and proficiency as mentors for students of diverse backgrounds and identities. |  | (Continuing)
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.3) - Expand mentoring in deep technical skills to help empower students, especially BIPOC students and all women and gender non-conforming students. These groups are underrepresented in IT professions and these skills are important for potential future pathways. | Vince Patone/Enterprise Team | (Continuing)
|  | Develop Mentorship Skills and Pipeline to Library and IT Careers (1.1.3.4) - Educate ourselves about how to support LITS students in equitable and inclusive professional development models, including by learning from students and co-creating model work environments with them that they can take into their future endeavors. |  | (Continuing)
Data and Assessment (3.2)
|  | Analyze MISO data disaggregated by race/ethnicity to assess whether we have disparities in levels of satisfaction or importance (positive outcome, further discussion and analysis will grow out of initial analysis) (3.2.1) - LITS already collects data from students and employees via the biannual MISO survey, regular service improvement feedback requests, and an annual faculty interview program. We’ll continue to gather, review, and act on this data. Our Director of Assessment and Assessment Working Group will guide our thinking about how to make meaningful use of these rich data sets and how to connect these data sources with disaggregated demographic data and more specific studies to inform our continuous movement toward equitable and inclusive programs, services, resources, and spaces. | Dave Consiglio and Assessment WG | FY21 Q4 | FY21 Q4 | √
Data and Assessment (3.2.2) - Examples of the kinds of questions we want to address include: Who is /is not participating in our Intensives, workshops, and other programs? Which students are / are not using the library? How do we gather data on those potential gaps and address any disparities that we find?
Data and Assessment (3.2.3) - We want to assess through a Racial Equity Impact Analysis our current practices for gathering feedback, asking such key questions as who are we talking to? how are we getting feedback? how do we portray our offerings for the community? Some of these are areas where representative focus groups may give us important perspective and insights.
Data and Assessment (3.2.4) - We want to build on the research Alex Pfundt has done around students’ feelings of self-efficacy around research practices.
Data and Assessment (3.2.5) - We’re interested in any insights we can gain from the College’s belongingness studies and campus climate studies, especially looking to the data for places where we can bridge gaps for Black, Indigenous, and other students of color.
Data and Assessment (3.2.6) - We believe in the power of stories in addition to the importance of aggregate data. We want to hear about impacts on students’ lives (positive and negative) of our offerings and their general experience of the College as they move through their educational journeys, and we hope those stories over time will show that the current high-priority College actions and local LITS actions land well and change students’ experiences for the better. We're interested in taking a pulse using appropriate psychology/affective measures to compare and contrast outcomes across groups and across time. How do we make sure our current and future efforts are landing with the concerns that community members are raising? What other data can we gather or draw upon to measure students’ sense of the impact of efforts underway at the institutional level and at the LITS level to see how the energy that’s invested is landing and to assess how we might need to shift course to meet our goals?
Data and Assessment (3.2.7) - We want to advocate for the College reviewing annually with the community how they are relating to our Equity, Inclusion, and Anti-Racism goals. Questions to ask might include: Did you engage with any of these initiatives? And did you find them valuable? Every year the College reports on initiatives in a more concerted way, and we're seeing a way we could take it to the next level with outreach and engagement to hear how initiatives are landing with those they’re designed to serve. Action Item: Gina will take these ideas to senior leadership.
|  | Data and Assessment (3.2.8) - Those who don't work actively with students in their regular work have a goal of volunteering to do senior exit interviews, recognizing that progress is seen in the eyes of the student and that listening to students in this annual process is a way to contribute to understanding from students’ perspectives how the College is doing. | Gina Siesing (forward invitation) and all LITS staff | FY21 Q4 | FY21 Q4 (and subsequent years) | √
Description, Metadata and Cataloguing (3.3)
Description, Metadata and Cataloguing (3.3.1) - We will continue to revise and augment the cataloguing and descriptive language that is used for our collections, working locally and in conjunction with consortial/regional and national efforts to update subject headings, as well as other classification terms and metadata, so that they are historically and culturally appropriate. This includes the removal of descriptors that are problematic and replacing them with updated and appropriate language; for example, TriCo librarians participated locally in making the change from “illegal aliens” to “undocumented immigrants” as part of a national movement to change this Library of Congress subject heading.
Description, Metadata and Cataloguing (3.3.2) - We will support students’ development of ethical and technical facets of digital competencies as they work with us on projects to revise and augment metadata that enables discovery of our rich collections and further study of their complex contexts. An example in this context is the work of Special Collections cataloging the children’s book collection and engaging students in this project, using an anti-racist catalog as a guideline for the original descriptions in our metadata.
Description, Metadata and Cataloguing (3.3.3) - Tied to our next goal, we will review and enhance as needed the accessibility of our collection discovery platforms and finding aids, as well as the accessibility guidelines and implementation for the content stored within these platforms. We included robust accessibility review and enhancement into our recent implementation project for the TriCollege Libraries Digital Collections platform (https://digitalcollections.tricolib.brynmawr.edu/), and we will do the same for legacy and future platforms. An example of the way we would enhance accessibility of the collection objects within the platforms would be to ensure we have appropriate and descriptive metadata following WCAG guidelines, such as alt tags for images and other best practices.
Description, Metadata and Cataloguing (3.3.4) - We will articulate a series of defined projects to move this work forward and will partner with BMC grants officers to seek potential funding in support of this labor-intensive and important work.
Inclusive and Accessible Collections and Ongoing Research (3.4)
Inclusive and Accessible Collections and Ongoing Research (3.4.1) - Special Collections is informing everything the department does with an equity, inclusion, and anti-racism lens. This year this includes ways of thinking about summer internships for students, framing of the fall exhibition, and how we build our collections. Special Collections will facilitate community engagement around our draft “Legacies of Colonialism and Racism in Special Collections” document in the upcoming year as a frame for demystifying the historical practices of special collections, making clear that special collections are open and welcoming and available for the full community to explore and study, and inviting in continuing research and learning projects around our phenomenal and complex collections and their contexts.
Inclusive and Accessible Collections and Ongoing Research (3.4.2) - We’ll continue to acquire and highlight the work of diverse authors in our general library collections, as well as the work of BIPOC artists and makers and community members in our special collections.
Inclusive and Accessible Collections and Ongoing Research (3.4.3) - We’ll continue to strengthen digital collections finding aids toward greater accessibility of collections. This work includes making more of the information we have public-facing and gathering more useful data surrounding the history of our collections and how they were acquired. This also includes creating new partnerships with communities represented in Bryn Mawr collections and collaborative continued research into the best practices for cultural representation, care, and preservation of collections from the perspective of their cultures of origin so we’re not just imposing ours. In each case, this will include determining if, and if so how, we care for a community’s materials in the Bryn Mawr collections.
College Histories Projects (3.5)
|  | College Histories Projects (3.5.1) - Current projects include the Who Built Bryn Mawr? project, where LITS is a partner with the President’s Office; faculty in History and History of Art; Museum Studies; College Communications; and Alumnae/i Relations & Development; among others. The first phase of Who Built Bryn Mawr? was launched this year in Canaday Library and online, and next phases of which will continue this summer and beyond. This project ties to broader goals of surfacing, documenting, and publishing richer and more diverse stories of those who have been important to the formation of the College throughout its history and building our archives for future scholarship and discovery by way of documenting the collegiate experience from the student perspective. |  |  |  | √
College Histories Projects (3.5.2) - Building digital collections is a priority for us, particularly archives that represent the collegiate experience from students’ perspectives. Recent projects include the Jewish Mawrters and Perry House oral histories projects and the Bryn Mawr Strike Collective digital collection. This includes proactively helping to archive the ephemeral, especially for the groups that weren’t part of dominant cultures at the time they participated as members of the Bryn Mawr College community.
College Histories Projects (3.5.3) - We will continue to support innovative and sustainable forms of scholarly publishing and engaged conversation so that the research that is ongoing finds the broadest possible audience. One of the important benefits of the research into College histories is the chance for all of us – employees, students, alumnae/i, families, and friends of the College - is the chance to learn a lot of new and rich history that was not available prior to the research projects that students, faculty, and staff are conducting under the umbrella of College histories work. These are opportunities to expose parts of the unique collections of Bryn Mawr that have not been exposed, for those things that are exposed to be put into context, and also for us to expose gaps in the collections that also teach us and that in some cases we can remediate.
Accessibility (3.6)
|  | Accessibility (3.6.1) - We contributed recently to articulation of the College’s new accessibility policy, and as next steps we’ll work to provide education around the policy and current accessibility standards to guide our implementation of tools, resources, and services in LITS. We’ll contribute as participants in the Accessibility Leadership Committee to articulating College standards for Universal Design for Learning (UDL) to guide the community in creating fully accessible and inclusive courses and learning experiences. | Jenny Spohrer (EAST)
|  | Accessibility (3.6.2) - We will also share information about accessibility related to the tools we support for the community. | Grace Cipressi (EAST)
|  | Accessibility (3.6.3) - We will draw on accessibility expertise within LITS to review and update our published resources, such as the LITS web presence, LibGuides, our KnowledgeBase/Techdocs, Digital Collections, etc. | Michael Harris (Web Services), et al.
|  | Accessibility (3.6.4) - As a service enhancement in supporting students with disabilities, we plan to develop with the Dean’s Office proactive outreach to incoming students before they get to campus, including information about adaptive technologies they may need, resources available on campus, etc. | Grace Cipressi (EAST)
|  | Accessibility (3.6.5) - We will continue to play a leadership role in advocating for accessibility policies and practices for the College and expert staff will continue to provide accessibility consultation and support for colleagues across campus who are creating and adopting new tools or resources. | Grace Cipressi (EAST), Michael Harris (Web Services), et al.
Accessibility (3.6.6) - We’ll continue to partner with College Communications to support accessibility of the College website.
|  | Accessibility (3.6.7) - We have audited the accessibility of many of our physical spaces, including the libraries, as part of an overall study conducted by the Accessibility Leadership Committee, and we will continue to work with Facilities Services and the Director of Access Services to enhance accessibility of physical spaces we manage. As we renovate spaces, we will pay particular attention to accessibility as a guiding principle. | Gina Siesing, Grace Cipressi, Jennifer Spohrer (LITS ALC members)
Welcoming Spaces and Sense of Belonging (3.7)
Welcoming Spaces and Sense of Belonging (3.7.1) - One of the ways we aim to ensure the libraries are welcoming spaces is by way of the displays of books by BIPOC authors or focused on topics of race and culture as a way to highlight the presence of BIPOC voices across our library collections and as a way to invite exploration of meaningful topics. We will engage students in selection and display of these spotlighted library collections.
Welcoming Spaces and Sense of Belonging (3.7.2) - Another way we aim to ensure our spaces are welcoming is by way of student-curated or co-curated exhibitions focusing on College histories. Key examples include the current Who Built Bryn Mawr? exhibition on the first floor of Canaday Library and Digital Color on Ancient Stone in the Carpenter Library Digital Media and Collaboration Lab, the installations associated with the renaming of Thomas Hall to Old Library, and the 2015 Backtalk: Exposures, Erasures, and Elisions of the Bryn Mawr College African Art Collections exhibition across the first-floor lobby, Class of 1912 Rare Book Room, and second-floor gallery of Canaday. These collections within our buildings and across campus will continue to be a major focus of our work helping to transform Bryn Mawr as a space.
|  | Welcoming Spaces and Sense of Belonging (3.7.3) - We aim to improve the public art displayed in the libraries and across campus, drawing on our Special Collections and the MakerSpace where community members are producing new work. Our Curator of Art and Artifacts will partner with colleagues across LITS and with community members to remove some of our collections from storage to meaningful display in our public spaces with a goal of giving Bryn Mawr public art increased attention and diversification. We’ll focus here on convening stakeholders to move such projects forward collaboratively, and we’ll also contribute to such projects convened by others such as the current Monument Lab partnership initiated by the President’s Office. | Carrie Robbins (SpecColl), et al.
Welcoming Spaces and Sense of Belonging (3.7.4) - We will work actively to debunk the common perception that Special Collections are “special” in the sense of being secret, exclusionary, elitist, or otherwise inaccessible. The Bryn Mawr special collections are a teaching and learning collection that are treasures of the full community, stewarded by a multi-disciplinary team whose primary mission is to support meaningful community engagement with the collections, including through courses, research projects, guided tours, Friday Finds events where students and others share what they’ve discovered, etc. We are at the ready to provide orientation to special collections and the possibilities for working with these unique resources, and we will continue to engage the community proactively in thinking about the legacies, current state, and possible futures of the Bryn Mawr collections.
Welcoming Spaces and Sense of Belonging (3.7.5) - As information specialists, we are deeply aware of the ways words and semantic representation matter in creating inclusive or exclusive environments and resources, and we have a particular focus through the Information Literacy program led by Research and Instruction Libraries to support students in thinking about critical evaluation and constructive production of information sources. We will continue to expand our partnerships with academic programs to integrate information literacy into the curriculum in support of student research at all levels, and we will continue to host information education and action programs such as the Wikipedia-thons where the BMC community can contribute to correcting bias in public information resources.
Accessible Resources (3.8)
Accessible Resources (3.8.1) - We will continue to review community feedback and to make process improvements wherever we discover that there are barriers to accessing LITS resources or support.
Accessible Resources (3.8.2) - We will review our middleware platforms through which we create and distribute resources, including LibGuides, KnowledgeBase, and digital collections platforms – to ensure that these are accessible.
Accessible Resources (3.8.3) - As we migrate to a new KnowledgeBase for how-to, support, and other help-oriented information, we will aim for the highest possible standard of accessibility and ease of discovery, following standards and enlisting the community in user experience testing with an eye to ensuring representation of underrepresented groups in our accessibility and usability reviews.
Accessible Resources (3.8.4) - Technology, software, and data are critical resources for the learning, teaching, research, and administrative work we do across the College. We will work to identify any places where community members have limited access to information technology resources and will do all we can to reach robust universal access. This includes accessibility and affordability of the resources, as well as the baseline of shared awareness of what is available and how to seek support in cases where resources are lacking or not obvious.
Inclusive and Accessible Programs (3.9)
Inclusive and Accessible Programs (3.9.1) - We will regularly invite evaluation of programs we offer to seek suggestions of ways to improve program accessibility and inclusivity.
Inclusive and Accessible Programs (3.9.2) - We’ll review data about participation in programs such as Intensives in partnership with Career and Civic Engagement to determine whether there are any disparities in participation, whether based on race/ethnicity, socioeconomic status, or other factors. If we find disparities in participation or in outcomes related to our programming (digital competencies, information literacy, etc.), we will propose interventions to correct those disparities and will work with relevant stakeholders to ensure we’re closing the gap in ensuring more accessible, inclusive programs.
How We Invest our Budget Money (3.10)
|  | How We Invest our Budget Money (3.10.1) - We are currently integrating diversity, equity, and inclusion questions and review into our vendor evaluation and IT procurement processes. | Bill Kenny and LITS Managers
|  | How We Invest our Budget Money (3.10.2) - Within library acquisitions, we’ll integrate a new focus on purchasing books from Black-owned and other BIPOC-owned bookstores and will seek partnerships with local community bookstores. | Berry Chamness (CMD)
Digital Divide and Tech/Data/Information Justice (3.11)
|  | Digital Divide and Tech/Data/Information Justice (3.11.1) - We will integrate this digital/tech/data/information justice lens more specifically into the frameworks of our Digital Competencies and Information Literacy programs. | Jenny Spohrer (EAST) and Alex Pfundt (RIS)
Digital Divide and Tech/Data/Information Justice (3.11.2) - We will educate students and community members about the non-neutrality of technology, data, and information and will integrate into our programs opportunities for engaging in anti-bias practices in the realms of technology, data, and information work.
Digital Divide and Tech/Data/Information Justice (3.11.3) - Across the disciplines of LITS, we are from professions where we think actively about these kinds of questions: what are the assumptions built into the resources we design, the tools we build? Where are the digital divide disparities within our own Bryn Mawr community, and how do we close those gaps? How can we influence broader technology, data, and information practices? Examples of topics might include data privacy issues, bias built into algorithms, and minimal computing possibilities (as one approach to address the digital divide and to model universal access to technology and data in an educational context).
Digital Divide and Tech/Data/Information Justice (3.11.4) - We will hold LITS cross- discipline/cross-department think tanks around ethics and justice in tech/data/information and identify ways to educate about these issues and about justice-oriented practices. We would then want to design community intensives or teach-ins around these same issues and practices.
Transparency in our practices/communication (3.12)
Transparency in our practices/communication (3.12.1) - Transparency in our practices and how we structure ourselves organizationally on the back-end to facilitate shared awareness and communication within LITS and for the broader community
Transparency in our practices/communication (3.12.2) - Ways each team names intentions (communications and function) and plans -> accountability in the college -> sharing out our plans
Transparency in our practices/communication (3.12.3) - Making sure we have a window into college administration
Transparency in our practices/communication (3.12.4) - Communicating in real time -> this can feel vulnerable vs. presenting polished final communications, but is a valuable long-term change
Transparency in our practices/communication (3.12.5) - Raise awareness for the EIAR efforts we’re making. Too often our efforts to advance anti-racism are not especially visible or transparent to the outside community. Gain advice from College Communications or the LITS CWG about how to de-clutter our websites and improve access to resources we already have but don’t necessarily make public (in Spec Coll, for example, resources for different types of research, materials handling, exhibition making, etc.)
Professional Development and Training (3.13)
|  | Professional Development and Training (3.13.0) - Develop curriculum of professional development for LITS staff - Initial DEIA/Anti-Racism Foundations sessions for departments (3.13.0) | DEI Team and CIO Direct Reports | FY20 Q4 | FY21 Q2 | √
Professional Development and Training (3.13.1) - We have participated in past College professional development opportunities, such as the Race Matters Institute focus on staff recruitment, the Cornell Interactive Theatre Ensemble workshops on reducing implicit bias, and the Stir Fry seminar, and will continue to engage in these opportunities and to integrate what we learn into our local practices, as we have in updating our staff hiring practices and student employee hiring practices.
Professional Development and Training (3.13.2) - Educating ourselves is key because of power we have in working relationships with students as employees, interns, and learners and because we serve a community of people who are different from ourselves and want to do that with awareness and skill. We also learn in deep ways from Bryn Mawr students and fellow employees, for example in the Trans 101, Religious Literacy, and Dialogues on Race learning opportunities offered by students and in Teach-ins and Community Days of Learning in student-led and staff-led sessions.
Professional Development and Training (3.13.3) - We are committed to sharing our understanding of best practices in equity, inclusion, and anti-racism with student employees through our training for them as part of their jobs and committed to partnering with student employees to create robust and trustworthy channels for them to provide feedback to their supervisors toward enhancing the equity, inclusiveness, and intersectional anti-racism of their work environments. We aspire to co-create model work environments that students will want to replicate as they move out into their future careers.
Professional Development and Training (3.13.4) - As we engage in shared professional development in facets of equity, inclusion, and intersectional anti-racism, we will continue to identify how equity, inclusion, and anti-racism goals of the College connect directly or indirectly with each of our jobs and service areas.
Professional Development and Training (3.13.5) - One facet of our professional development will be learning about College histories through the projects LITS supports as a way to serve as resources who can help disseminate this new information with those we work with across campus and beyond.
Reducing our own marginalization as staff within the caste system of the College (3.14)
Reducing our own marginalization as staff (3.14.1) - Even as we at LITS invest our efforts in helping to make the College a more inclusive, equitable, and anti-racist institution for its students and faculty and full community, we will be mindful of the position of staff within the traditional caste hierarchies of Bryn Mawr and higher education more generally and will advocate for the recognition of our worth within the College, for respectful interactions across roles, and for equitable pay and benefits and inclusion for staff in College policies, practices, and culture.
|  | Review and improve LITS staff recruiting and hiring practices (work with Race Matters Institute (RMI) and HR and contributions to new Staff Recruitment Guidebook with diversity, equity, and inclusion lens; preparation for hiring managers and search committees with new College guidance | DEI Team and LITS managers | FY20 Q1 | FY20 Q4 | √
Information Security and Stewardship
|  | Update Incident Response Protocol | Gina Siesing | FY20 Q1 | FY20 Q2 | √
|  | Enhance/redesign Information Security Education Program | Melissa Cresswell | FY20 Q4 | FY21Q4 | √
|  | Implement vulnerability testing for infrastructure and systems | Vince Patone | FY20 Q3 | FY21 Q2 | √
|  | Complete whole disk encryption rollout | Katie Surkin | FY20 Q1 | FY23 Q4
Holistic Mentorship and Professional Development of Students
|  | Continue to articulate student employment as professional development (including Digital Competencies and Information Literacy development) | Katie Surkin (with Jenny Spohrer, Alex Pfundt, and student employee supervisors across LITS) | FY20 Q2 | FY22 Q4
|  | Mentor students in internships and research projects (Educational Technology Interns, Digital Scholarship Fellows and Graduate Assistants, Histories of the College projects, etc.) | LITS managers with mentors across LITS | FY20 Q1 | FY24 Q4
|  | Implement and assess split fellowship/service model for Digital Scholarship Graduate Assistants program | Alice McGrath | FY20 Q1 | FY20 Q4 | √
|  | Partner with Career & Civic Engagement Center to scaffold student reflection and articulation practices; using Domain of One's Own host eportfolios | Jenny Spohrer | FY20 Q1 | FY24 Q4
|  | Contribute to Customs, ESem, THRIVE, 360°, POSSE, and Advising programs | LITS managers and staff across teams | FY20 Q1 | FY24 Q4
Planning and Organizational Development
|  | Develop 5-year Strategic Roadmap for LITS | Gina Siesing | FY19 Q3 | FY20 Q2 | √
|  | Develop local strategic plans within Enterprise, CEP, and TLR | Vince Patone, Melissa Cresswell, TLR Leadership Team | FY20 Q3 | FY21 Q1
|  | Re-activate quarterly BMC senior staff prioritizing meetings as part of maintaining up-to-date strategic plan | Gina Siesing | FY20 Q3 | FY21 Q1
|  | Focus on service portfolio management practices (service design and enhancement, service assessment, service sunsetting) | Melissa Cresswell | FY20 Q2 | FY21 Q4 | √
|  | Leadership and professional development targeted to goals for the organization and staff | Gina Siesing | FY20 Q1 | FY24 Q4 | √
|  | Succession planning for LITS | Gina Siesing | FY20 Q2 | FY21 Q2
II. Teaching, Learning, and Research
Canaday Library Renovation
|  | Pre-planning with LITS -> Deliver Vision Statement and Business Case to President Cassidy | Gina Siesing/Eric Pumroy | FY18 Q2 | FY20 Q1 | √
|  | Case study within broader campus space planning study led by Nina Bisbee/Facilities with external consultants | Gina Siesing with Berry Chamness, Eric Pumroy, and Katie Surkin | FY20 Q1 | FY20 Q4 | √
|  | Evaluating, cataloging, and re-housing of art works, artifacts, rare books, manuscripts & archives in anticipation of move, and seeking funding for this work | Eric Pumroy | FY20 Q1 | FY24 Q4 | On hold while we assess how pandemic has affected likely timeline.
|  | Planning for special collections storage and exhibition spaces in new building | Eric Pumroy | FY20 Q1 | FY24 Q4 | On hold while we assess how pandemic has affected likely timeline.
|  | Program design and concept design for Canaday | Gina Siesing | FY21 Q3 | FY22 Q2 | On hold while we assess how pandemic has affected likely timeline.
|  | Fundraising for Canaday renovation as part of College campaign | Gina Siesing | FY22 Q2 | FY24 Q4 | On hold while we assess how pandemic has affected likely timeline.
|  | Renovation of the library | Gina Siesing | FY24 Q1 | FY25 Q1 | On hold while we assess how pandemic has affected likely timeline.
Data Science Program Support
|  | Discovery for Data Science Program Support (classroom/lab needs assessment; RStudio pilots; LITS role in lab support) | Jenny Spohrer | FY20 Q1 | FY20 Q4 | √
|  | Service Modeling/Planning for Data Science Program Support (Jupyter/RStudio Service Modeling, planning classroom/lab renovation) | Jenny Spohrer | FY20 Q3 | FY21 Q1 | √
|  | Classroom/lab space renovation as needed | Dave Consiglio | FY21 Q2 | FY23 Q4
|  | Discovery for Research/Collections Data Science Program support (start date contingent on program planning; director hire, etc.) | Kate Blinn | FY21 Q2 | FY22 Q2
|  | Service planning for LITS role in Lab/Center Support (if needed) | Jenny Spohrer/Dave Consiglio/Kate Blinn | FY21 Q2 | FY23 Q2
|  | Integrating data science education in Digital Scholarship Program (data ethics, collections as data projects, programming support) | Alice McGrath | FY21 Q2 | FY22 Q2
Digital Asset Management and Preservation
|  | Implement Islandora as primary TriCo digital asset management and preservation platform (migrate from ContentDM and DSpace legacy systems) | Natalie Shilstut | FY20 Q2 | FY21 Q3 | √
|  | Electronic records management policy drafted and implemented | Allison Mills | FY20 Q1 | FY22 Q4
|  | Implementing the Digital Preservation Policy | Natalie Shilstut | FY20 Q4 | FY22 Q4
|  | EmbARK software update and migration to new servers | Howard Ding/Joanna Davidson | FY20 Q3 | FY20 Q4 | √
|  | Create infrastructure to support short and medium-term digital projects related to the History of the College | Alicia Peaker | FY20 Q3 | FY20 Q4 | √
|  | Drafting and implementing the digital projects sunsetting policy | Alice McGrath | FY20 Q3 | FY21 Q2 | √
|  | Migration from Islandora 7 to Islandora 8 | Natalie Shilstut | FY21 Q4 | FY22 Q4
|  | Additional migrations from various platforms (e.g., bepress) to consolidate our digital assets | Gina Siesing with Peg Seiden and Terry Snyder | FY21 Q3 | FY21 Q4
Digital Competencies for BMC Students
|  | Iteratively refine Digital Intensives offerings, adding one on Web Design and Development, aligning with Center for CCE Career Exploration focus | Jenny Spohrer | FY20 Q1 | FY20 Q4 | √
|  | Collaborate with departments and programs to integrate digital scholarship into curricula | Alice McGrath | FY20 Q2 | FY24 Q4
|  | Provide opportunities for students to showcase their digital scholarship research at the Digital Scholarship Summer Symposium and other venues | Alice McGrath | FY20 Q1 | FY24 Q4
|  | Expand programming integration with Civic Engagement/Praxis/Summer of Service | Jenny Spohrer | FY20 Q1 | FY21 Q2
|  | Iteratively test, refine and get stakeholder feedback on Digital Competencies articulation rubric | Jenny Spohrer | FY21 Q1 | FY21 Q4
|  | Expand training and outreach for Domain of One's Own | Alice McGrath | FY20 Q1 | FY24 Q4
|  | Integrate opportunities into Digital Competencies website via navigation to examples of different genres of opportunity with associated news stories | Jenny Spohrer | FYQ3 | FY21 Q2 | √
|  | Develop and pilot menu of digital competency-related workshops that can be offered in classes and outreach for LITS workshop services | Jenny Spohrer | FY21 Q1 | FY21 Q4
|  | Scale/implement Digital Competencies articulation rubric | Jenny Spohrer | FY22 Q1 | FY22 Q4
|  | Develop/plan half-semester and Praxis opportunities that involve Digital Competencies (e.g., graphic design, working with data, serious games) | Jenny Spohrer | FY20 Q3 | FY23 Q4
|  | Develop and host personal digital archiving workshops for students and student groups | Allison Mills | FY20 Q2 | FY21 Q4
Enable Contemporary Forms of Scholarship
|  | Facilitate interdisciplinary communities of learning and practice for digital scholarship | Alice McGrath | FY20Q1 | FY24 Q4
|  | Build capacity for supporting emerging research technologies and methods through staff training | Vince Patone/Jenny Spohrer | FY20 Q2 | FY24 Q4
|  | Partner with campus groups to support public-facing and social-justice-oriented research projects | Eric Pumroy | FY20 Q2 | FY22 Q4
|  | Grow Digital Scholarship Research Institute for Tri-Co faculty to build skills and community (originated by Alicia Peaker; upcoming phase led by Mike Zarafonetis at HC) | Alice McGrath | FY20 Q1 | FY24 Q4
|  | Support faculty, staff, and graduate students in improving digital teaching, learning, and research activities through the Digital Bryn Mawr seed grant program | Jenny Spohrer | FY20 Q1 | FY24 Q4
Information Literacy at Scale for BMC Students
|  | Expand structured opportunities for students (from introductions to library work for first-year students to IL learning for students within their majors) | Alex Pfundt | FY20 Q1 | FY24 Q4
|  | Foster community, and particularly faculty, buy-in and understanding of IL | Alex Pfundt | FY20 Q1 | FY24 Q4
|  | Advocate for pre-major focus via transformation of Esem or similar curricular intervention building on support of Curriculum Committee and Department Chairs | Alex Pfundt | FY20 Q3 | FY24 Q4
Lecture Capture
|  | Replace Tegrity (end of life) | Jenny Spohrer | FY19 Q3 | FY20 Q2 | √
|  | Panopto lecture capture system implementation | Vickie Karasic | FY20 Q2 | FY21 Q1 | √
Collier Phase Two Renovation
|  | LITS planning with Facilities department and architects | Gina Siesing/Camilla MacKay | FY20 Q1 | FY20 Q2 | √
|  | Preparation for construction: withdrawal/moving of library collections | Berry Chamness | FY21 Q3 | FY21 Q4
|  | Collier construction | Gina Siesing/Camilla MacKay | FY22 Q1 | FY22 Q3 | Possible delay of classroom construction element to future phase
Moodle Future-Proofing and Planning
|  | Moodle MFA | Jenny Spohrer | FY19 Q1 | FY21 Q1 | √
|  | Internal service modeling to develop more sustainable support services and management plan | Jenny Spohrer | FY20 Q3 | FY21 Q2 | √
|  | Exploration of data analysis tools and integrations | Jenny Spohrer | FY21 Q2 | FY22 Q1
|  | Moodle Exploratory Analysis and Design (in conjunction with ERP/SIS discovery) | Jenny Spohrer | FY22 Q1 | FY22 Q3
|  | Implementation based on EAD | Jenny Spohrer | FY22 Q3 | FY23 Q4
Material Culture
|  | Develop guide to teaching primary source literacy | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Articulate options for teaching with collections | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Develop model for advising on exhibitions across campus | Eric Pumroy | FY20 Q3 | FY21 Q4
|  | Develop opportunities for students to have longer-term engagement with collections through post-bac program | Eric Pumroy | FY21 Q1 | FY22 Q4
|  | Design and Implment Critical Making initiative | Bronwen Densmore | FY21 Q1 | FY23 Q1
College History
|  | Oral History Guideines | Eric Pumroy | FY20 Q2 | FY20 Q4 | √
|  | Praxis or 360 Project - Develop guidelines for course-connected projects in the College Archives & identify potential projects | Eric Pumroy/Allison Mills | FY20 Q2 | FY21 Q4
|  | Revise records management policy | Allison Mills | FY20 Q1 | FY20 Q4 | √
Museum Studies
|  | Create structure for bringing in specialized expertise through program of adjunct faculty and short-term consultants | Monique Scott | FY20 Q2 | FY22 Q4
Continue to ensure stability and discoverability of collections
|  | Integrate Islandora with Primo/Alma | Howard Ding/Joanna Davidson | FY22 Q3 | FY23 Q1
|  | ArchivesSpace upgrade | Howard Ding | FY20 Q1 | FY20 Q3 | √
|  | Integrate Islandora with ArchivesSpace | Howard Ding/Joanna Davidson | FY22 Q3 | FY23 Q1
III. Enterprise Data, Systems, and Interfaces
Next-Generation Enterprise Ecosystem for Bryn Mawr
|  | Continued review of Core ERP terrain (particular focus on SIS developments) | Vince Patone | FY19 Q1 | FY22 Q4
|  | Enrollment Discovery and Planning | Gina Siesing | FY19 Q3 | FY19 Q4 | √
|  | PowerFAIDS implementation for Financial Aid with associated data integrations and business process enhancements | David Sturgis | FY20 Q1 | FY20 Q2 | √
|  | ARD Discovery and Planning | Gina Siesing | FY19 Q4 | FY20 Q4 | √
|  | PeopleSoft Logging - Data about What's Currently Happening | Vince Patone | FY19 Q3 | FY20 Q4 | √
|  | Evaluation and Selection of Alumnae/i Relations and Fund-raising platform(s) | Vince Patone | FY21 Q1 | FY21 Q1 | √
|  | Implementation planning for ARD with selected vendor | Vince Patone | FY21 Q2 | FY21 Q3 | √
|  | Implementation and Migration for ARD with associated data integrations and business process enhancements | Vince Patone | FY21 Q3 | FY22 Q2
|  | Evaluation and Selection of Core ERP (HR/Payroll/Finance/SIS+) | Vince Patone | FY22 Q1 | FY22 Q3
|  | Implementation of HR/Payroll/Finance modules of ERP | David Sturgis | FY22 Q4 | FY23 Q4
|  | Develop strategy for SIS with Haverford | Gina Siesing | FY23 Q3 | FY24 Q2
|  | Implement shared BiCo SIS module in new ERP | Gina Siesing | FY24 Q3 | FY25 Q4
Data Governance and Business Intelligence
|  | Data/system Inventory update with ISC | Gina Siesing | FY19 Q3 | FY20 Q1 | √
|  | Data analytics introduction with Senior Staff | Gina Siesing | FY19 Q4 | FY19 Q4 | √
|  | Partner with President, Senior Staff, IR, ISC to articulate Institutional Data Governance Model | Gina Siesing | FY20 Q3 | FY21 Q2
|  | Establish Dashboarding Pilot with Tableau/HelioCampus or similar data reporting/analytics platform | Gina Siesing | FY21 Q1 | FY21 Q4
|  | Evaluate data analytics and business intelligence solutions to match institutional and operational goals | Vince Patone | FY21 Q3 | FY22 Q1
|  | Implement data analytics and BI service including campus education model | Vince Patone | FY22 Q3 | FY23 Q4
Web and Mobile Interfaces
|  | Support College website redesign project via ESC and core project team participation | Chelsea Lobdell | FY20 Q1 | FY22 Q3
|  | Website infrastructure upgrade - migrate our current Drupal installation to the BMC VMWare environment [We migrated instead to cloud hosting via Acquia to support business continuity.] | Chelsea Lobdell | FY20 Q2 | FY20 Q4 | √
|  | Migration from Drupal 7 to Drupal 8 during or subsequent to College website redesign project | Chelsea Lobdell | FY20 Q4 | FY22 Q4
|  | TriCo Course Data - Store data in BMC Drupal instance and create BMC URL for students (Registrar's Office) | Vince Patone | FY20 Q3 | FY21 Q1 | √
|  | Migrate Find directory to Drupal - includes faculty CVs (Provost's Office) | Chelsea Lobdell | FY20 Q3 | FY21 Q1
|  | Retire bascom legacy web server with appropriate community engagement | Chelsea Lobdell | FY21 Q2 | FY22 Q1
|  | Review business case for implementing PeopleSoft Fluid | David Sturgis | FY20 Q2 | FY20 Q3 | √
|  | Implement PeopleSoft Fluid for SIS if business case compelling [Fluid will be required with next upgrade cycle.] | David Sturgis | FY21 Q1 | FY21 Q3
|  | Assess other strategic mobile interface enhancement needs for BMC | Vince Patone | FY21 Q4 | FY22 Q2
|  | Develop roadmap for any BMC mobile projects identified through assessment | Vince Patone | FY22 Q3 | FY22 Q4
|  | Continue to assess and improve accessibility throughout all campus computing systems | Vince Patone | FY20 Q1 | FY24 Q4
Storage
|  | Implment TriCo Storage (digital asset preservation storage, access storage, and temporary workflow storage) | David Bertagni | FY20 Q2 | FY20 Q3 | √
Overall Infrastructure
|  | Review Infrastructure and Systems current state and develop strategic roadmap for future updates and investments | Vince Patone | FY21 Q1 | FY22 Q2
IV. Client Experience and Support
Create seamless support for clients
|  | Service Experience and Delivery Team identifies a simple set of expectations and practices around which we can orient our approach to service | Katie Surkin | FY19 Q4 | FY21 Q4 | √
|  | Based on regular analysis of client feedback identify service experience enhancement projects | Katie Surkin | FY21 Q1 | FY24 Q4 | √
Develop robust consultation services for academic and administrative colleagues across campus
|  | Business Analysis and Solutions Team builds existing and potential consultative practices to maturity and defines service model across various LITS contexts | Melissa Cresswell | FY19 Q4 | FY20 Q4 | √
Help the community to navigate a fast-evolving technology terrain
|  | Help the community become increasingly comfortable and empowered using technology (outreach, peer-to-peer learning opportunities) | Melissa Cresswell | FY22 Q3 | FY24 Q4
|  | Streamline and humanize the client support experience and increase engagement with next generation models and tools (knowledge base, ticketing, ITSM/PPM, service catalog, in-time support innovations) | Melissa Cresswell | FY20 Q3 | FY22 Q2
|  | Build and enact models for systematically gathering feedback from the community (i.e. listening tour, ticket surveys) | Melissa Cresswell/Katie Surkin | FY20Q1 | FY21 Q2 | √
Provide contemporary tools and services appropriate to the Bryn Mawr College context
|  | Analyze and enhance choice and affordability in desktop hardware (procurement models and computer replacement program) | Bill Kenny | FY20 Q2 | FY23 Q4
|  | Move to next generation software delivery (virtualization, Windows management, Microsoft 365 deployment, lab environments) | Melissa Cresswell/Kordell Alexander | FY20 Q4 | FY24 Q4